Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 28 July 2026 |
| --- | --- |
| Team ID |  |
| Project Name | FreelanceHub – Full Stack Freelance Marketplace (MERN) |
| Maximum Marks | 5 Marks |

# Product Backlog & Sprint Planning

| Sprint | Functional Requirement (Epic) | User Story No. | User Story / Task | Story Points | Priority | Team Member |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration | USN-1 | As a user, I can register as a client or freelancer using my username, email and password. | 3 | High | Ritesh Kolate |
| Sprint-1 | Authentication | USN-2 | As a user, I can log in using my email and password. | 2 | High | Ritesh Kolate |
| Sprint-1 | Authentication | USN-3 | As a user, my password is hashed with bcrypt and protected APIs use JWT authentication. | 5 | High | Ritesh Kolate |
| Sprint-1 | Authorization | USN-4 | As a user, I can access only the features allowed for my role (Client, Freelancer or Admin). | 3 | High | Ritesh Kolate |
| Sprint-1 | Freelancer Profile | USN-5 | As a freelancer, I can create and update my profile to showcase my skills. | 3 | Medium | Ritesh Kolate |
| Sprint-2 | Project Management | USN-6 | As a client, I can post a project with title, description, budget, skills and deadline. | 3 | High | Ritesh Kolate |
| Sprint-2 | Project Management | USN-7 | As a client, I can update and delete my projects. | 2 | Medium | Ritesh Kolate |
| Sprint-2 | Project Discovery | USN-8 | As a freelancer, I can browse all open projects. | 2 | High | Ritesh Kolate |
| Sprint-2 | Project Discovery | USN-9 | As a freelancer, I can search projects by title or description and filter by skill. | 3 | Medium | Ritesh Kolate |
| Sprint-2 | Applications | USN-10 | As a freelancer, I can submit an application with my bid, estimated days and cover letter. | 5 | High | Ritesh Kolate |
| Sprint-2 | Applications | USN-11 | As a client, I can view received applications and approve or reject them. | 5 | High | Ritesh Kolate |
| Sprint-2 | Find Freelancers | USN-12 | As a client, I can browse freelancer profiles. | 2 | Medium | Ritesh Kolate |
| Sprint-3 | Project Workflow | USN-13 | As a freelancer, I can submit completed work for an approved project. | 3 | High | Ritesh Kolate |
| Sprint-3 | Project Workflow | USN-14 | As a client, I can mark a submitted project as completed. | 2 | High | Ritesh Kolate |
| Sprint-3 | Reviews & Ratings | USN-15 | As a client, I can rate and review the freelancer for a completed project. | 3 | Medium | Ritesh Kolate |
| Sprint-3 | Chat | USN-16 | As a user, I can send and view messages within a project. | 5 | Medium | Ritesh Kolate |
| Sprint-3 | Notifications | USN-17 | As a user, I can view notifications and mark them as read. | 3 | Medium | Ritesh Kolate |
| Sprint-3 | Dashboard | USN-18 | As a client or freelancer, I can view my dashboard with project and activity statistics. | 5 | High | Ritesh Kolate |
| Sprint-3 | Admin Panel | USN-19 | As an administrator, I can view platform statistics and manage user status. | 5 | High | Ritesh Kolate |
| Sprint-3 | Admin Panel | USN-20 | As an administrator, I can moderate projects, applications and reviews. | 3 | Medium | Ritesh Kolate |
| Sprint-3 | Deployment | USN-21 | As a user, I can access the application online. | 3 | High | Ritesh Kolate |

# Project Tracker, Velocity & Sprint Schedule

Since the project duration is 15 days, divide it into 3 sprints of 5 days each.

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 16 | 5 Days | 15 Feb 2026 | 19 Feb 2026 | 16 | 19 Feb 2026 |
| Sprint-2 | 22 | 5 Days | 20 Feb 2026 | 24 Feb 2026 | 22 | 24 Feb 2026 |
| Sprint-3 | 32 | 5 Days | 25 Feb 2026 | 01 Mar 2026 | 32 | 01 Mar 2026 |

# Velocity

Total Story Points = 70

Total Sprints = 3

Average Velocity per Sprint:

70 ÷ 3 = 23.3 ≈ 23 Story Points/Sprint

Average Daily Velocity:

70 ÷ 15 = 4.7 ≈ 5 Story Points/Day

# Burndown Chart Data

| Day | Remaining Story Points |
| --- | --- |
| 1 | 70 |
| 2 | 65 |
| 3 | 60 |
| 4 | 55 |
| 5 | 50 |
| 6 | 45 |
| 7 | 40 |
| 8 | 35 |
| 9 | 30 |
| 10 | 25 |
| 11 | 20 |
| 12 | 15 |
| 13 | 10 |
| 14 | 5 |
| 15 | 0 |

## Project Summary

| Metric | Value |
| --- | --- |
| Total User Stories | 21 |
| Total Story Points | 70 |
| Project Duration | 15 Days |
| Total Sprints | 3 |
| Sprint Duration | 5 Days |
| Average Velocity | 23 Story Points/Sprint |
| Average Daily Velocity | ≈ 5 Story Points/Day |